## Overview-Summer and Fall
NCTR PROGRAM DIAGNOSTIC: PROGRAM DEVELOPMENT PLAN (PDP)
Based on data from the Diagnostic, NCTR and its partner programs collaboratively develop a Program Development Plan (PDP). The PDP articulates where and how programs would like to improve by setting annual program goal(s), determining the supports needed to reach those goals, and identifying the measures that will be used to assess progress towards meeting the goals.
PDP Development Date: |  | 7.26.16; Updated throughout summer/fall
Program Name: |  | ABC Residency
PROGRAM STRENGTHS |  |  | PROGRAM GROWTH AREAS
Mentor Selection: We have an intensive mentor selection experience that includes an observation, interview, feedback from students, and principal recommendation. |  |  | Mentor Professional Development: We need to better support our mentors so that we move from support that is reactive to support that is proactive.
District Partnerships: We have multiple district partnerships that have been formally vetted to ensure they align to the mission and vision of ABC Residency |  |  | District Partnerships: We need to better manage partnerships including how to ensure all partners are engaged and involved in decision-making, and continually invested in ABC Residency
Resident Competencies (Professionalism): We have residents engage in a "360 process" which helps us to understand how residents are managing the program in terms of courseload, preparation, etc. |  |  | Resident Performance Benchmarks: We need to measure resident progress individually and collectively - our formative "performance" benchmarks need strengthening.
PROGRAM IMPROVEMENT GOALS
GOAL | RELATED NCTR COMPETENCY AREAS/STANDARD/GOAL(S) |  | RELATED DRIVERS | ACTIVITIES/SUPPORTS/STRATEGIES |  |  | SUCCESS INDICATORS |  | PROGRESS MONITORING (ONGOING)
[5 empty] | PROGRAM | NCTR | What | By When | EVIDENCE OF PROGRAM PROGRESS: FALL/WINTER
Develop a multiple measures approach to assessing resident performance and effectiveness aligned to professional and performance expectations. | Residency programs are continuous learning organizations that use data to drive improvement. |  | 2. Engage in authentic continuous improvement | What: | TBD* | Peer to Peer Opportunities: Data Strategy Group (description below) | TBD | TBD | TBD*
| Residency programs prepare residents to become student-ready teachers of record. |  |  |  |  | Quarterly cross-Network virtual convenings with differentiated followup (NCTR consulting, affinity groupings) to improve strategies for collecting data and using data to improve resident, teacher educator and graduate practice, and overall program effectiveness
Strengthen engagement and investment of each district partner in order to develop a strategic and sustainable revenue and cost model | Teacher educators prepare residents to become student-ready teachers of record. |  | 3. Ensure their own teacher educators are effective | What: | Strengthen Program Director's knowledge and skills in mentor development | Peer to Peer Opportunities: Teacher Educator Professional Development and Instructional Rounds | Designing and implementing a full mentor development/support scope and sequence that improves mentor practice as teachers and teacher educators; 100% of particpants agree that the PD strengthened their practice as teachers and teacher educators; 100% of residents with participating mentors report high satisfaction with their mentors as teachers and coaches; after two years of fully implementing the scope & sequence, resident performance on core instructional competencies addressed in mentor PD improves as evidenced by program performance assessments | By end of 2018 | Consultant hired
[5 empty] | Hire a consultant to support the building out of this work | TEPD Opportunity |  |  | Program Director reading/reviewing research
[5 empty] | Design structure for mentor PD | Problem of Practice
Leverage strong mentors to serve as models/strengthen practice at specific schools
Program Director understands/learns more about the research on mentor training
Strengthen Mentor capacity by providing rich professional development, consistent feedback and targeted support to strengthen practice as teacher educators | Residency programs are partnerships among school districts, universities, and other stakeholders to prepare and retain effective teachers. |  | 4. Driven by school systems and the communities they serve | What: | TBD* | Strategic Support: Partnership module to strengthen partnership, sustainability and resident effectiveness (description below) | TBD* | TBD* | TBD*
One NCTR facilitated virtual consultancy with an affinity group of programs to share challenges and identify improvement strategies; access to an online portal page with relevant resources updated bi-monthly follow up to measure progress and impact
*Program leadership worked with NCTR in mid-September to prioritize goals and develop an achieveable action plan for the program's highest priority goal. Activities and success indicators for remaining goals will be the focus of January PDP progress call.

## Prioritization Exercise-Fall
Prioritization Exercise: Identifying Immediate, Short and Longer Term Goals
Steps:
1) Perform impact/doability (cost, effort, risk) exercise for all goals
2) Chart goals on matrix
3) Determine immediate, medium, and longer term goal
Goal |  | Impact | Doability
1 | Develop a multiple measures approach to assessing resident performance and effectiveness aligned to professional and performance expectations. |  | Cost:
|  |  | Effort: |  |  | IMPACT/DOABILITY MATRIX
|  |  | Risk: | high | 4 |  |  | Goal 3
2 | Strengthen engagement and investment of each district partner in order to develop a strategic and sustainable revenue and cost model |  | Cost: | IMPACT | 3
|  |  | Effort: |  | 2
|  |  | Risk: | low | 1
3 | Strengthen Mentor capacity by providing rich professional development, consistent feedback and targeted support to strengthen practice as teacher educators | Mentor teachers are the backbone of the program - they drive school sites, school leadership, etc. Without them and without them being strong, the struggle will be real. Produce better residents | Cost (human and financial): More funding in the mentor piece at the IHE so the cost, financially, is not as high - but are trying to hire a field director although lost office manager |  |  | 1 | 2 | 3 | 4
|  |  | Effort: IHE is securing a consultant for Kery with background in mentor development; IHE is interested in developing a mentor cert program and making the supports more formal |  |  | hard | DO-ABILITY |  | easy
Risk: short staffed -- no more field director - supporting 1st and 2nd year teaches in the field; besides being director, Kery is over all of it
4 | Additional goals: Strengthening resident recruitment numbers, and supporting with Content area certification exams | If we don't focus on it, we won't have enough people in our program to focus on anythng else | Cost:
Effort:
Risk:
Decision:
Immediate Goal: |  | Strengthen Mentor capacity by providing rich professional development, consistent feedback and targeted support to strengthen practice as teacher educators
Medium Term Goal:
Longer Term Goal:
Longer Term Goal:

## Root Cause And Action Planning-
Root Cause to Action Exercise: Identifying Root Causes, Success Indicators, and Action Steps
Steps:
1) Perform root cause analysis for high priority/immediate goal to identify the "AHA" or "true root cause" of the goal
2) Turn the "AHA" into a Success Indicator for the goal (how will success be measured?)
3) Populate action plan to facilitate goal achievement
Root Cause Analysis
Goal | Why | Why | Why | Why | AHA
Strengthen Mentor capacity by providing rich professional development, consistent feedback and targeted support to strengthen practice as teacher educators | Mentor selection process has always been strong. Over time though, we stopped following procedures. | Short-cuts started to happen in the selection process due to time and capacity. | Due to mentor selection issues, mentor retention became a bigger challenge and therefore there is now a wider mentor experience playing field (newer mentors with more experienced mentors) | Current mentor PD does not take into account mentor needs. We now need to take a differentiated approach with mentor PD rather than "one-size fits all" training | Vision of mentor training has not been not program-driven (perhaps too narrow)...we are now thinking about a holistic mentor training model.
|  | NCTR | Program
Success measured by: | When: | Supports | Action Step | How | Who | By When | Anticipated Challenges/ Supports | Potential Solutions
Designing and implementing a full scope and sequence for mentor development and support. | By FY-18 | Rounds; Teacher Ed PD Opportunity; Network examples | Strengthen Program Director's skills in the area of mentor development and support | Hire a consultant (IHE)
Participate in Instructional Rounds
|  |  |  | Understandithe research about mentor training | NCTR can share some articles
|  |  | Design structure (framework?) for Mentor PD | Usie the design template introduced at Symposium
Teaching works Opportunity in November
Observe mentors implementing actionable strategies
|  |  | Develop strategies to measure impact of Mentor PD on Residents | Consider and decide methods to measure (e.g. video observations and debriefs?)
|  |  | Leverage strong mentors to strengthen mentor practice at their schools | Move to hub school model where there are more mentors at one site
Next Steps:
-NCTR: Send Program Director Scope and Sequence of mentor development that exist in the network, research on Mentor PD
-Program Director will consider TW opportunity (can she attend, who should attend?)
-Program Director will review the action plan: add to and revise

## CAI-Summer
COMPETENCY AREA I: PARTNERSHIP & PROGRAM SUSTAINABILITY (INITIAL PDP and DIAGNOSTIC DATA ANALYSIS CALL NOTES, JULY 2016; call recording has more detail)
On which Standards and Goals did your program perform most favorably?
On which Standards and Goals did your program perform less favorably?
Why might your program have performed more or less favorably in some areas over others? What surprised you about the data?
What are the implications of the data for your program's design, implementation and impact?
REFLECTIONS
FUNDING/SUSTAINABILITY: We expanded beyond just one district because we are always looking to grow in terms of partnership and we wanted to create a model where districts were investing in our residents. Smaller districts were willing to invest in stipend for Residents rather than the larger district. . DATA: So much of the data is summative, big reports at end. Narrative type things, big surveys, etc. Not "how is it going along the way," more formative benchmark data that can help reflect and adjust. It was "now that you are done, what did you think?" Every cohort is different with different needs this summative data only goes so far. Trying to create benchmark data collection approaches for residents. It wasn't measurable. What data gets collected on mentors and coaches and field supervisors and course instructors? Helps us get at who needs an improvement plan, lets us get to know our residents. IHE: Our IHE Partner has new leadership, changed approach to how all candidates in STEM would be ABC residents - change in philosophy -- impact of program not seen as large for IHE-- only 20 residents - they won't let us have a separate IHE cohort -- low recruitment numbers have made our program less impactful. Now integrating into scope and sequence of larger Teacher Prep. etc.
NEW THOUGHTS OR CONSIDERATIONS
Strengthen partnership with distrtict partners: Lay out what the partnership is, what expectations exist for district partners. Think we could do a better job of having district understand what our strategic plan is. Need to diversify our funding sources. Data sharing and reporting -- having not only meetings to frontload but also to share impact data. (maybe even identify common metrics for impact data with district partners). Develop a multiple measures approach to assessing resident peformance and effectiveness aligned to BOTH professional and performance expectations.

## CAII-Summer
COMPETENCY AREA II: RESIDENCY DEVELOPMENT (INITIAL PDP and DIAGNOSTIC DATA ANALYSIS CALL NOTES, JULY 2016; call recording has more detail)
On which Standards and Goals did your program perform most favorably?
On which Standards and Goals did your program perform less favorably?
Why might your program have performed more or less favorably in some areas over others? What surprised you about the data?
What are the implications of the data for your program's design, implementation and impact?
REFLECTIONS
RESIDENT RECRUITMENT. Need to make sure Residents pass the tests. Other Residency Programs have done innovative things in this area and we are also looking into that. MENTOR RECRUITMENT: We have a multiple measures approach to mentor recruitment. This year we left a lot of good mentors on the table b/c resident recruitment was so low.
NEW THOUGHTS OR CONSIDERATIONS
Upping resident recruitment numbers. Content exam.

## CAIII-Summer
COMPETENCY AREA III: RESIDENCY EXPERIENCE (INITIAL PDP and DIAGNOSTIC DATA ANALYSIS CALL NOTES, JULY 2016; call recording has more detail)
On which Standards and Goals did your program perform most favorably?
On which Standards and Goals did your program perform less favorably?
Why might your program have performed more or less favorably in some areas over others? What surprised you about the data?
What are the implications of the data for your program's design, implementation and impact?
REFLECTIONS
What competencies is the program looking for when the "we do" starts? Then, lets talk about the co-development of the first lead unit - -how do you plan it and get to the point where you teach one lesson a day. Two lead units a year - one in fall and one in spring. Spring -- also co developed but resident takes the lead. What additional supports do mentors receive? What data gets collected on mentors and coaches and field supervisors and course instructors? PD -- this year will be a change. Last year had a mentor development director. This year that falls under Program Director's responsibility. Staff reduction - Program Director now in charge of mentor development. Workshops last year were about how to use the protocols, having difficult conversations, problmes come up - "in time" support or "reactive" -- not really a PD. That is something Program Director wants to add.
NEW THOUGHTS OR CONSIDERATIONS
Want to integrate technologoy to strengthen the feedback process. Challenge is around getting everyone feedback in the right time - video and rehearsal can help with this. Residents need more gradual. Not a lot of time to get more specific feedback on behalf of residents. Looking to learn more in the area mentor development.

## CAIV-Summer
COMPETENCY AREA IV: GRADUATE IMPACT (INITIAL PDP and DIAGNOSTIC DATA ANALYSIS CALL NOTES, JULY 2016; call recording has more detail)
On which Standards and Goals did your program perform most favorably?
On which Standards and Goals did your program perform less favorably?
Why might your program have performed more or less favorably in some areas over others? What surprised you about the data?
What are the implications of the data for your program's design, implementation and impact?
REFLECTIONS
All residents got hired; lots of need for SPED; in district they are given early contracts - really strong partnership in terms of hiring - program graduates are teacher leaders in district -- not going to become teacher leaders just yet - brand new baby teachers ..do they have opportunties to become TLs -- program grads are new teachers --
NEW THOUGHTS OR CONSIDERATIONS
CA IV questions could be more relevant if they are layered -- what supports are you providing in year 1 or year 2 or year 3 grads. How programs define "teacher leader" can vary -- to PD - its are you a dept. lead, instructional coach, etc. - those are 3+ year stuff -- our grant usually ends 2 years out.